## Project Planner
Select a period to highlight at right. A legend describing the charting follows. | [14 empty] | Period Highlight: |  |  |  | Actual (beyond plan) | [5 empty] | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan)
UV LED Controller Project Planner | [6 empty] | Today | 2022-04-06 | [8 empty] | mar | [6 empty] | Alp | [26 empty] | may | [31 empty] | June | [29 empty] | july | [30 empty] | Aug | [30 empty] | Sep
| Mass production Plan1: In Jan 2023. |  |  |  |  | Update:Blue Caution:Red
Mass production Plan2: In Nov 2022. 30weeks from Apr 2022 for long lead time parts.
Mass production Plan3: In XXX 2023. 52weeks from Apr 2022 for long lead time parts.
| ACTIVITY / Task |  |  |  | Tag | DESCRIPTION / PURPOSE | HR | Due Date | PLAN START | PLAN DURATION (Wks) | ACTUAL START | ACTUAL DURATION | Number of worker | Man week | PERCENT COMPLETE | [16 empty] | Function design | [51 empty] | Prototype design | [41 empty] | Product design
[16 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 |  | 155
[16 empty] | 3.29 | 3.3 | 3.31 | 4.01 | 4.02 | 4.03 | 4.04 | 4.05 | 4.06 | 4.07 | 4.08 | 4.09 | 4.10 | 4.11 | 4.12 | 4.13 | 4.14 | 4.15 | 4.16 | 4.17 | 4.18 | 4.19 | 4.2 | 4.21 | 4.22 | 4.23 | 4.24 | 4.25 | 4.26 | 4.27 | 4.28 | 4.29 | 4.30 | 5.01 | 5.02 | 5.03 | 5.04 | 5.05 | 5.06 | 5.07 | 5.08 | 5.09 | 5.10 | 5.11 | 5.12 | 5.13 | 5.14 | 5.15 | 5.16 | 5.17 | 5.18 | 5.19 | 5.20 | 5.21 | 5.22 | 5.23 | 5.24 | 5.25 | 5.26 | 5.27 | 5.28 | 5.29 | 5.30 | 5.31 | 6.01 | 6.02 | 6.03 | 6.04 | 6.05 | 6.06 | 6.07 | 6.08 | 6.09 | 6.10 | 6.11 | 6.12 | 6.13 | 6.14 | 6.15 | 6.16 | 6.17 | 6.18 | 6.19 | 6.20 | 6.21 | 6.22 | 6.23 | 6.24 | 6.25 | 6.26 | 6.27 | 6.28 | 6.29 | 6.30 | 7.01 | 7.02 | 7.03 | 7.04 | 7.05 | 7.06 | 7.07 | 7.08 | 7.09 | 7.10 | 7.11 | 7.12 | 7.13 | 7.14 | 7.15 | 7.16 | 7.17 | 7.18 | 7.19 | 7.20 | 7.21 | 7.22 | 7.23 | 7.24 | 7.25 | 7.26 | 7.27 | 7.28 | 7.29 | 7.30 | 7.31 | 8.01 | 8.02 | 8.03 | 8.04 | 8.05 | 8.06 | 8.07 | 8.08 | 8.09 | 8.10 | 8.11 | 8.12 | 8.13 | 8.14 | 8.15 | 8.16 | 8.17 | 8.18 | 8.19 | 8.20 | 8.21 | 8.22 | 8.23 | 8.24 | 8.25 | 8.26 | 8.27 | 8.28 | 8.29 | 8.30 | 8.31 | 9.01 | 9.02 | 9.03 | 9.04 | 9.05 | 9.06 | 9.07 | 9.08 | 9.09 | 9.10 | 9.11 | 9.12 | 9.13 | 9.14 | 9.15 | 9.16 | 9.17 | 9.18 | 9.19 | 9.20 | 9.21 | 9.22 | 9.23 | 9.24 | 9.25 | 9.26 | 9.27 | 9.28 | 9.29 | 9.30
Check | A. FUNCTION DESIGN |  |  |  |  | Prepare 20set parts for Function Design. It is including Dep quotation. Only make PCB on Function design. |  |  | 1 | 45
| 1. Hard ware Design |  |  |  | Hard | Design UV controller circuit and UV LED circuit | Thủy |  | 1 | 21 |  |  | 2 | 4
| 1.1 Design PCB test buck circuit |  |  |  |  | Design buck convert 1.2A/5V | Thủy
|  | 1.1.1 Purchase BOM of buck circuit |  |  |  | Thiếu BOM | Hân, Thủy | 2022-04-06 | 1 | 1
|  | 1.1.2 Design buck PCB by altium and order PCB |  |  |  |  | Thủy | Done | 1 | 5 |  |  |  |  | 100%
|  | 1.1.3 Solder PCB with part |  |  |  |  | Thủy | Done | 5 | 1
|  | 1.1.4 Make test case |  |  |  |  | Thủy | 2022-04-06 | 6 | 1
|  | 1.1.5 Test buck PCB |  |  |  |  | Thủy | 2022-04-06 | 6 | 1
|  | 1.1.6 Make doccument design for buck circuit |  |  |  |  | Thủy | 2022-04-06 | 7 | 1
| 1.2 Design PCB test MCU circuit |  |  |  |  | design a PCB only with Mcu for test mcu circuit (power, ADC ref, oscilator….) design and test firmware | Thủy
|  | 1.2.1 Purchase BOM of test MCU circuit |  |  |  | Thiếu BOM | Hân, Thủy | 2022-04-06 | 1 | 1
|  | 1.2.2 Design test MCU PCB by altium and order PCB |  |  |  |  | Thủy | Done | 8 | 7
|  | 1.2.3 Solder test MCU PCB with part |  |  |  |  | Thủy |  | 14 | 1
|  | 1.2.4 Make doccument design for test MCU circuit |  |  |  |  | Thủy |  | 14 | 1
| 1.3 Design HMI circuit |  |  |  |  | design LED and button circuit fit with current LED controller box. | Thủy
|  | 1.3.1 Purchase BOM of HMI circuit |  |  |  | Thiếu BOM | Hân | 2022-04-06 | 1 | 1
|  | 1.3.2 Design HMI PCB by altium and order PCB |  |  |  |  | Thủy |  | 15 | 6
|  | 1.3.3 Solder HMI PCB with part |  |  |  |  | Thủy |  | 21 | 1
|  | 1.3.4 Make test case of HMI PCB |  |  |  |  | Thủy |  | 21 | 1
|  | 1.3.5 Test HMI PCB |  |  |  |  | Thủy |  | 21 | 1
| 1.4 Design full functions circuit V1 |  |  |  |  | combine MCU circuit and buck circuit and other circuit to run all function like current controller without fit of box | Thủy
|  | 1.4.1 Purchase BOM of full function circuit |  |  |  | Thiếu BOM | Hân, Thủy | 2022-04-06 | 1 | 1
|  | 1.4.2 Design full PCB V1 by altium and order PCB |  |  |  |  | Thủy |  | 7 | 10
|  | 1.4.3 Solder full PCB V1 with part |  |  |  |  | Thủy |  | 17 | 2
|  | 1.4.4 Make Hardware test case |  |  |  |  | Thủy |  | 17 | 1
|  | 1.4.5 Test full PCB Hardware |  |  |  | only test hardware do not contain firmware | Thủy |  | 18 | 1
|  | 1.4.6 Make doccument design for full function V1 |  |  |  |  | Thủy |  | 17 | 2
| 1.5 Design JIG for LED header and external |  |  |  |  | design JIG for all inspection after | Thủy |  | 17 | 5
|  | 1.5.1 Design LED header JIG |  |  |  |  | Thủy |  | 17 | 5
|  | 1.5.2 Design ext JIG |  |  |  |  | Thủy |  | 17 | 5
| 2. Firm ware Design |  |  |  | Firm | without being exactly dimension in order to program | Triều |  | 4 | 34 |  |  | 2 | 4
| 2.1 Code with MCU kit | [5 empty] | Triều |  | 4 | 6
|  | 2.1.1 code MCU with oscilator |  |  |  |  | Triều | Done | 4 | 1
|  | 2.1.2 code GPIO |  |  |  |  | Triều | Done | 5 | 1
|  | 2.1.3 code ADC |  |  |  |  | Triều | Done | 6 | 1
|  | 2.1.4 code PWM |  |  |  |  | Triều | Done | 7 | 1
|  | 2.1.5 code I2C |  |  |  |  | Triều | Done | 8 | 1
|  | 2.1.6 code data flash (like EEPROM) |  |  |  |  | Triều | 2022-04-08 | 9 | 1
| 2.2 Code with test MCU PCB | [5 empty] | Triều |  | 15 | 1
|  | 2.2.1 Check driver code with new PCB |  |  |  |  | Triều |  | 15 | 1
| 2.3 Code with full function PCB | [5 empty] | Triều |  | 10 | 28
|  | 2.3.1 Check driver code with new PCB |  |  |  |  | Triều |  | 19 | 1
|  | 2.3.2 Code 4 x 7 seg led control |  |  |  |  | Triều |  | 20 | 1
|  | 2.3.3 Read all button data |  |  |  |  | Triều |  | 10 | 1
|  | 2.3.4 Read and write data with led header (I2C) |  |  |  |  | Triều |  | 11 | 1
|  | 2.3.5 Reading, setting ext terminal |  |  |  |  | Triều |  | 12 | 1
|  | 2.3.6 Control LED header for lighting |  |  |  |  | Triều |  | 21 | 1
|  | 2.3.7 Save current data to data flash |  |  |  |  | Triều |  | 22 | 1
|  | 2.3.8 Code system state diagram |  |  |  |  | Triều |  | 23 | 14
|  |  | 2.3.3.1 Code errState |  |  |  | Triều |  | 23 | 1
|  |  | 2.3.3.2 Code Standby state |  |  |  | Triều |  | 24 | 4
|  |  |  | a. Set life time alarm substate |  |  | Triều |  | 24 | 1
|  |  |  | b. Read operation time, temp substate |  |  | Triều |  | 24 | 1
|  |  |  | c. Read Dim, emiss time substate |  |  | Triều |  | 25 | 1
|  |  |  | d. Lock front end substate |  |  | Triều |  | 25 | 1
|  |  |  | e. Set channel substate |  |  | Triều |  | 26 | 1
|  |  |  | f. Mode select substate |  |  | Triều |  | 26 | 1
|  |  |  | g. Set outmode substate |  |  | Triều |  | 27 | 1
|  |  |  | h. Set DIM, emiss time substate |  |  | Triều |  | 27 | 1
|  |  | 2.3.3.3 Code output control state |  |  |  | Triều |  | 28 | 1
|  |  | 2.3.3.4 Code Stable function |  |  |  | Triều |  | 29 | 4
|  |  | 2.3.3.5 Code connect all state |  |  |  | Triều |  | 33 | 5
| 3. Function test |  |  |  | Test | current control, HMI, I2C communication, feedback function… | Thủy |  | 38 | 8 |  |  | 2 | 6
|  |  | 3.1 Complete the test case base on MRT test case |  |  |  | Thủy |  | 38 | 2
|  |  | 3.2 Test Design base on test case |  |  |  | Thủy |  | 40 | 5
|  |  | 3.3 Write test report |  |  |  | Thủy |  | 45 | 1
Check | B. PROTOTYPE DESIGN
| 1. Hard ware Design |  |  |  | Hard | circuit , After stage 1, we design exactly dimension that fit into Moritex's current box | Thủy |  | 22 | 7 |  |  | 2 | 4
|  | 1.1 Check board Shape and fix position of some parts |  |  |  |  | Thủy |  | 22 | 1
|  | 1.2 Drawn board into this Shape andrepair error on function design. Order PCB |  |  |  |  | Thủy |  | 23 | 5
|  | 1.4 Solder PCB with all part |  |  |  |  | Thủy |  | 28 | 1
|  | 1.5 Test hardware without Code |  |  |  |  | Thủy |  | 29 | 1
| 2. Firm ware Design |  |  |  | Firm | program , Beside, the circuit that we design will be test to achieve | Triều |  | 46 | 4 |  |  | 2 | 4
|  | 2.1 Check old firmware with new PCB |  |  |  |  | Triều |  | 46 | 1
|  | 2.2 edit code if need |  |  |  |  | Triều |  | 47 | 3
| 3. Mechanical Design |  |  |  | Case box | case box | Thi |  | 17 | 14 |  |  | 1 | 2
| 3. Prototype testing |  |  |  | TEST | standard (EMI,...). After that, we will implement stress test | Triều, Thủy |  | 46 | 11 |  |  | 3 | 3
|  |  | 3.1 Function test |  |  |  | Thủy |  | 46 | 3
|  |  |  | 3.1.2 Test with test case |  |  | Thủy |  | 46 | 3
|  |  | 3.2 Stress test at HTK | [5 empty] | 49 | 8
|  |  |  | 3.2.1 Make stress test case |  |  | Thủy |  | 49 | 1
|  |  |  | 3.2.2 Test with test case |  |  | Thủy |  | 50 | 7
| 4. EMI Testing |  |  |  | EMC | In Vietnam | Triều, Thủy |  | 50 | 7 |  |  | 2 | 2
|  |  | 4.1 make list test standard for EMC |  |  |  | Thủy |  | 29 | 1
|  |  | 4.2 Test all in Viet Nam |  |  |  | Thủy, Triều |  | 50 | 7
Check | C. PRODUCT DESIGN | [7 empty] | 57 | 68
| 1. Hard ware Design |  |  |  | Hard | Final stage, we will verify design to mass production | Thủy |  | 57 | 17 |  |  | 2 | 2
|  | 1.1 Review test result, offer solution to repair error |  |  |  |  | Thủy |  | 57 | 3
|  | 1.2 Redrawn PCB |  |  |  |  | Thủy |  | 60 | 4
|  | 1.3 Order PCB on JLC |  |  |  |  | Thủy |  | 64 | 7
|  | 1.4 Solder PCB with all part |  |  |  |  | Thủy |  | 71 | 1
|  | 1.5 Test hardware with Code |  |  |  |  | Thủy |  | 72 | 1
| 2. Firm ware Design |  |  |  | Firm |  | Triều |  | 73 | 3 |  |  | 2 | 2
|  | 2.1 Check old firmware with new PCB |  |  |  |  | Triều |  | 73 | 1
|  | 2.2 Edit code if need |  |  |  |  | Triều |  | 74 | 2
| 3. Mechanical Modify |  |  |  | Case box |  | Thi |  | 57 | 14 |  |  | 1 | 2
| 4. Reliability Testing |  |  |  | EMC | In China Need to add schedule of shipment (VT-CN) | Triều, Thủy, Huy |  | 76 | 16 |  |  | 3 | 3
|  | 4.1 Test EMC in Viet Nam |  |  |  |  | Triều |  | 76 | 4
|  | 4.2 Prepare item to send to AGC |  |  |  |  | Thủy |  | 80 | 1
|  | 4.3 Send to AGC |  |  |  |  | Hân |  | 84 | 4
|  | 4.4 Wait result |  |  |  |  | Triều |  | 88 | 7
| 5. Back-up Period | [5 empty] | Triều, Huy, Thi |  | 95 | 23 |  |  | 3 | 6
| 6. Release the final design | [5 empty] | Triều, Thủy, Huy, Thi |  | 118 | 7 |  |  | 4 | 2
46